## Colour
PROJECT TITLE
Company name |  |  |  |  | Legend: |  | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2023-02-01 | [5 empty] | April | [27 empty] | May
Scrolling Increment: | 65 | time axis 2023-04-07 to 2023-06-01
Milestone description | Category | Column1 | Progress | Start | Days | Column2 | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T
User Requirments Specification
Use Cases | Goal |  |  | 2023-02-06 | 4
Completion of requirments document | Milestone |  |  | 2023-02-09 | 1
Project Plan
Defining project scope and objectives | Goal |  |  | 2023-02-13 | 5
Approval of the project plan | Milestone |  |  | 2023-02-17 | 1
UML Class Diagram
Desigin of Uml | Goal |  |  | 2023-02-14 | 3
Finishing software design | Milestone |  |  | 2023-02-17 | 1
Development of an intermidiate version
Development of the program | Goal |  |  | 2023-02-27 | 7
Delivering Indermidiate Version | Milestone |  |  | 2023-03-05 | 2
Implementation web app
Implementing the Registration | Goal |  |  | 2023-03-06 | 4
Implementing the accounts | Goal |  |  | 2023-03-13 | 3
implementing the Login | Goal |  |  | 2023-03-20 | 4
implementing the shopping cart for logged in users | Goal |  |  | 2023-03-27 | 3
finish the login related stuff | Milestone |  |  | 2023-03-30 | 2
Implementation of Data Access Layer
Make data access for the Bikes | Goal |  |  | 2003-04-06 | 5
implement data access for accounts |  |  |  | 2023-04-17 | 4
Implementation of Shipping information |  |  |  | 2023-04-22 | 3
Implementation of Order History Page |  |  |  | 2023-04-25 | 4
Implementation of Orders In The win forms app |  |  |  | 2023-05-12 | 3
Return Functionality |  |  |  | 2023-05-15 | 4 | bar: 2023-04-11
Unit Testing |  |  |  | 2023-05-15 | 5
Implememtation of a coupon system |  |  |  | 2023-05-23 | 5
To add more data, Insert new rows ABOVE this one